VANTORA First Real Customer Deployment Plan

FMCG Van-Sales · Pilot, Reference Tenant & Certification Package

Generated 2026-06-10 · PR #311

# First Real Customer Deployment Plan

Objective: onboard the first real FMCG distributor onto VANTORA and

capture structured real-world feedback — not to add features and not to

scale. Success is measured in *learning and reliable daily operation*, not in

breadth.

Guiding principle: one distributor, one branch, 1–3 van reps, online-first,

behind KAKO_VAN_SALES (default OFF) + a per-company toggle. Go deep, observe

everything, change nothing on the platform during the pilot unless a blocker

forces it.

This plan sequences the certified pilot package and the

[Onboarding Package](./ONBOARDING-INDEX.md) into a dated, owned, measurable

deployment with an explicit feedback engine and a decision gate.

## 1. Scope & non-goals

In scope: deploy to production for one distributor; run the full

sell→collect→return→reconcile→close loop daily; capture feedback; decide

scale/iterate/pause.

Explicit non-goals (during the pilot):

❌ No new features / no schema changes (feedback is *captured*, not *built*).

❌ No multi-distributor rollout.

❌ No offline mode (Phase 6 is out of scope; route must have connectivity).

## 2. Select the first distributor

Pick for *learnability and low risk*, not size. Ideal profile:

| Criterion | Target |
| --- | --- |
| Size | 1 branch, 1–3 van reps, ~100–500 active customers |
| Route connectivity | Reliable mobile data (online-first) |
| Data quality | Clean, exportable master data (products, customers, prices) |
| Sponsorship | An engaged owner/GM + a hands-on supervisor |
| Appetite | Willing to run in-app, no off-book, and give candid feedback |
| Products | Single base UoM per SKU (multi-UoM deferred) |

Red flags → choose a different first customer: poor connectivity + offline

mandatory; messy/unavailable master data; no internal champion.

## 3. Roles & responsibilities (RACI)

| Activity | Distributor Owner/GM | Supervisor | Reps | VANTORA Deployment Lead | VANTORA Support |
| --- | --- | --- | --- | --- | --- |
| Sign-off & scope | A | C | I | R | I |
| Master data supply | R | C | I | A | I |
| Environment + activation | I | I | I | R/A | C |
| User onboarding & training | C | R | I | A | C |
| Go/No-Go decision | A | C | I | R | C |
| Daily operation | I | A | R | I | C |
| Reconciliation | I | R/A | I | I | C |
| Feedback capture | C | R | R | A | R |
| Issue triage/escalation | I | R | I | A | R |
| Scale/iterate decision | A | C | I | R | C |

R=Responsible · A=Accountable · C=Consulted · I=Informed.

## 4. Timeline (indicative, ~4 weeks)

| Phase | Duration | Outcome |
| --- | --- | --- |
| 0. Qualify & agree | 2–3 days | Customer selected, scope + success criteria signed, sponsor named |
| 1. Build (onboarding package) | 2–4 days | Master data imported, users + vans + pricing set, Readiness = READY |
| 2. Rehearse | 1 day | Supervised on-device dry-run passes; training delivered |
| 3. Go-live + Hypercare | 5 working days | Daily in-app operation; intensive support; daily feedback synthesis |
| 4. Stabilize | 2 weeks | Tapering support; weekly metrics; feedback backlog triaged |
| 5. Evaluate & decide | 2–3 days | Pilot report; scale / iterate / pause decision |

## 5. Prerequisites & environment

[ ] Production project provisioned; backups/observability on.

[ ] Company created (name, currency, country, tax number, logo).

[ ] KAKO_VAN_SALES=1; per-company is_enabled initially OFF until rehearsal passes.

[ ] Staging carries the reference tenant for side-by-side comparison.

[ ] Branch codes chosen (tenant-scoped numbering since 0268 — safe to reuse common codes).

[ ] Data export from the distributor's current system mapped to the

[import templates](./templates/README.md) (ERPNext/Odoo presets available).

## 6. Deployment runbook

Execute the [Distributor Onboarding Checklist](./DISTRIBUTOR-ONBOARDING-CHECKLIST.md)

end to end (it is the runbook). Summary:

Build — import branches → warehouses/vans → products → suppliers → routes

→ customers → users → opening stock → journey plans.

Configure — VAT + base price per SKU; assign vans to reps; approve

customers; set credit limits + payment terms; set discount cap.

Activate — per-company toggle ON; Readiness Diagnostic = READY (0 blockers).

Rehearse — one supervised on-device dry-run (open→sell→collect→return→

reconcile→close), all green; deliver Day-1 training.

Go-live — reps run their real day in-app; hypercare begins (§8).

## 7. Go / No-Go gate (sign-off required)

GO only when all are TRUE (from the certified package):

[ ] KAKO_VAN_SALES ON + per-company is_enabled = true.

[ ] Each rep has an assigned, stocked van; one base UoM per SKU.

[ ] Every SKU resolves a positive price; customers approved/on-branch with

credit limits; return reasons active.

[ ] Roles assigned; reconciliation owned by supervisor/warehouse-keeper.

[ ] Readiness = READY; one on-device dry-run passed.

[ ] Route connectivity adequate; rollback understood (one switch).

[ ] Feedback channels live (§9) and owners named.

Accountable sign-off: Distributor Owner/GM + VANTORA Deployment Lead.

## 8. Hypercare (go-live week)

On-call support during field hours; deployment lead reachable.

Daily standup (≤15 min): yesterday's sales/collections/returns posted

in-app? all days closed + reconciled? any rejections (credit/stock/price)? any

off-book activity? any new feedback items?

Daily feedback synthesis (§9) → triage → log → (only if a *blocker*) escalate.

Cadence + triage table: [Pilot Support Playbook](./PILOT-SUPPORT-PLAYBOOK.md).

## 9. Feedback capture plan (the core objective)

Capturing real-world feedback is the primary deliverable of this deployment.

### 9.1 Channels

| Channel | Who | Frequency |
| --- | --- | --- |
| Field feedback log (templates/feedback-log.csv) | Supervisor + deployment lead | Continuous (every item) |
| Daily standup notes | Deployment lead | Daily (hypercare) |
| Rep quick-pulse (3 questions: what blocked you? what was slow? what helped?) | Reps | End of each day (week 1) |
| Weekly review with sponsor | Owner/GM + lead | Weekly |
| In-app signals | Support | Continuous (audit log, rejection tokens, reconciliation variances, day-close coverage) |

### 9.2 What to capture (taxonomy)

Each item logged with: date, source (rep/supervisor/owner/support), category,

severity, area, description, document/error token, status, resolution/owner.

Categories: bug · usability · data · process · performance ·

training · feature-request · pricing · connectivity.

Severity: S1 blocker (can't operate) · S2 major (workaround exists) ·

S3 minor · S4 cosmetic/idea.

### 9.3 Handling rules (no platform changes mid-pilot)

S1 blocker → escalate immediately (T3); if no in-app workaround, consider

per-rep or full rollback (one switch) while triaging. *Only* an S1 justifies

a mid-pilot change.

S2–S4 → log only, do not build. These feed the post-pilot backlog and

the next strategic phase.

Every item gets a status: open → triaged → resolved/deferred.

### 9.4 Instrumented signals (objective, not just opinions)

Pull weekly from the system: in-app sales %, collection rate, return reasons

completeness, reconciliation variance, day-close coverage %, rejection

frequency by token (over_credit, insufficient_van_stock, price-0), cancelled/

corrected docs, GPS out-of-route exceptions. (See

[Week-1 Monitoring](../architecture/fmcg/PILOT-LAUNCH-PACKAGE.md#5-pilot-week-1-monitoring-guide).)

## 10. Success metrics & exit criteria

| Metric | Target |
| --- | --- |
| In-app sales (no off-book) | ≥ 95% of route sales |
| Day-close + reconciliation | 100% for 5 consecutive days |
| Stock accuracy (reconciliation variance) | ≥ 99% |
| AR / balance accuracy | 100% consistent |
| Returns via system with a reason | 100% |
| Cross-tenant / data-integrity incidents | 0 |
| Rep adoption | all reps operating independently |
| Feedback | logged, categorized, synthesized into a backlog |

Pilot is "successful" when: the exit criteria hold and the feedback

backlog is captured and prioritized — regardless of how many feature requests it

contains (those are the *point*, not a failure).

## 11. Risk register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Dirty/incomplete master data | Med | High | Validate via import dry-run; compare to reference tenant; fix before go-live |
| Reps revert to paper | Med | High | Supervisor enforces in-app; daily standup catches off-book; show value (instant docs) |
| Connectivity gaps on route | Low–Med | Med | Confirm coverage in qualification; online-first; defer offline (Phase 6) |
| Pricing mis-set → price 0 / wrong price | Low | High | Readiness Diagnostic blocks; verify 2–3 SKUs; server-authoritative pricing |
| Over-credit/stock rejections frustrate reps | Med | Low | Train on the meaning; collect-first workflow; tune limits |
| Branch-code overlap with other tenants | — | — | Resolved (tenant-scoped numbering, 0268) |
| Scope creep (requests → build mid-pilot) | Med | Med | Strict §9.3: log S2–S4, build nothing; decide post-pilot |

## 12. Rollback & contingency

Instant, non-destructive — one switch:

Pause the module: unset KAKO_VAN_SALES or per-company is_enabled=false.

Per-rep pause: unassign the rep's van.

Re-enable anytime; issued documents remain valid.

Full guide: [Rollback](../architecture/fmcg/PILOT-LAUNCH-PACKAGE.md#7-pilot-rollback-guide).

Trigger rollback only for an unresolved S1 blocker.

## 13. Communication plan

| Audience | Cadence | Owner | Content |
| --- | --- | --- | --- |
| Distributor sponsor (Owner/GM) | Weekly | Deployment lead | Metrics, feedback themes, decisions |
| Field team (reps/supervisor) | Daily (hypercare) | Supervisor | Standup, fixes, encouragement |
| VANTORA internal | Weekly | Deployment lead | Status, risks, backlog growth |
| Decision forum | End of pilot | Owner/GM + lead | Pilot report + scale/iterate/pause |

## 14. Decision gate — scale / iterate / pause

At pilot end, the deployment lead presents a Pilot Report (metrics vs §10 +

the categorized feedback backlog). The sponsor + lead decide:

SCALE — exit criteria met, no S1 open → roll out to more reps/branches,

then more distributors; feed the backlog into the next strategic phase.

ITERATE — mostly met with specific gaps → address top backlog items

(post-pilot, as planned development), then re-pilot the affected area.

PAUSE — exit criteria not met / sustained S1 → rollback, root-cause, replan.

## 15. Post-pilot synthesis (the lasting output)

Produce, from the captured feedback:

Pilot Report — metrics, what worked, what didn't, incidents.

Prioritized backlog — S2–S4 items ranked (effort × impact), tagged to a

future phase (e.g. Merchandiser/CS roles, brand/tax masters, offline Phase 6,

multi-UoM).

Onboarding refinements — fold real lessons back into the

[onboarding package](./ONBOARDING-INDEX.md) (templates, guides, timings).

Go/No-Go for scale.

The first deployment's job is to convert *assumptions* into *evidence*. Ship

nothing new during it; capture everything; decide with data.