VANTORA — Phase 1 Execution Plan (FMCG Pilot Readiness)

FMCG Van-Sales · Pilot, Reference Tenant & Certification Package

Generated 2026-06-10 · PR #311

# VANTORA — Phase 1 Execution Plan & Implementation Backlog (FMCG Pilot Readiness)

Goal: close the Phase-1 gaps that block an FMCG pilot — admin governance, GM/Admin separation, a

Collection Officer workspace, an Inventory Controller role, a full UI role QA, and mobile FMCG validation.

Tenant: Nile FMCG (DEMO) on vantora-staging, using the seeded 90-day dataset.

Status: PLAN ONLY — no implementation in this task; awaiting approval to start.

Effort unit = dev-day (one mid/senior full-stack engineer). Estimates assume the current schema and

the demo dataset; they include build + self-test, not external review.

## 0. Cross-cutting prerequisite (do first)

P1.0 — Reachable QA build (BLOCKER for P1.5 & P1.6).

The role-isolation RLS is already live, but the matching frontend code (scoped selectors + write guards)

and all Phase-1 UI changes must be on a reachable build for the QA/mobile items.

Deploy the claude/fmcg-sell-collect-loop code to a preview wired to vantora-staging.

Make it reachable for QA: disable Vercel SSO or add a password/bypass, ideally a temporary domain.

Confirm NEXT_PUBLIC_SUPABASE_URL/ANON_KEY point at vantora-staging.

Effort: 1d · Deps: none · Risk: exposure of demo data once public (mitigate with password

protection); no real customer data present so risk is low.

## 1. P1.1 — Company Admin governance (tenant-scoped)

Objective: a Company Admin can manage Branches, Users, Roles & Permissions, Warehouses *within their

own tenant* — without is_super_admin (a platform flag).

Current state (verified):

/settings/branches, /settings/users, /settings/permissions nav items are superAdminOnly; their

pages guard if (!ctx.isSuperAdmin) …; their server actions call requireSuperAdmin().

/settings/permissions edits global erp_role_permissions (super-admin territory).

Already tenant-admin-capable: /settings/staff (scoped RPC erp_company_staff + erp_can_manage_staff)

and /settings/authz (Authz Console) writing erp_company_role_permissions — RLS already allows

company_id = erp_user_company_id() AND erp_is_company_admin(company_id).

Warehouses (/warehouses): admin can already manage (RLS branch_id IN erp_user_branch_ids()).

Branch INSERT is blocked for tenant admin (RLS erp_branches_access checks id IN branch_ids, which a

*new* branch isn't). erp_roles create/edit is super-admin only (role *keys* are platform-managed).

Target state & tasks:

| Task | What | Effort |
| --- | --- | --- |
| P1.1a | Branches: nav superAdminOnly → perm: 'settings.branches'; page guard isSuperAdmin → has('settings.branches'); actions requireSuperAdmin() → requireCompanyAdmin() (new helper using erp_is_company_admin), scoped to erp_user_company_id(). | 1.5d |
| P1.1b | Branches RLS: add company-scoped INSERT/UPDATE/DELETE policy on erp_branches (and erp_regions/erp_areas) — company_id = erp_user_company_id() AND erp_is_company_admin(company_id). Migration. | 1.0d |
| P1.1c | Users: route tenant-admin "Users" to the existing `/settings/staff` (already scoped); enhance Staff to cover the full lifecycle a pilot needs — invite, assign role, assign branch, activate/deactivate, reset password. Keep /settings/users (global, is_super_admin editing) super-admin only. | 1.5d |
| P1.1d | Roles & Permissions: point tenant-admin "Roles/Permissions" to the Authz Console (/settings/authz, company-scoped). Verify it can: list roles, edit a role's company permissions, and (optional) clone/disable a role for the tenant. The global /settings/permissions stays super-admin only. | 1.0d |
| P1.1e | Warehouses: confirm admin access end-to-end (already RLS-supported); add nav clarity. | 0.25d |
| P1.1f | Security review of all new write paths (no cross-tenant escape). | 1.0d |

Total effort: ~5–6d · Deps: none (foundational) · Acceptance: Company Admin (not super-admin)

can create/edit a branch, invite a user + assign role/branch, edit a role's permissions, and manage

warehouses — all limited to their own tenant, verified by a second tenant being unaffected.

Risks: 🔴 Cross-tenant privilege escalation if a new branch/role/user policy or action isn't

company-scoped — this is the highest-risk item; gate every write on erp_is_company_admin(company_id) +

erp_user_company_id() and add a 2-tenant negative test. Role-*key* creation stays platform-only (by

design) — document that tenant admins customize permissions of existing roles, not invent role keys.

## 2. P1.2 — Separate GM from Company Admin

Objective: GM (operations leader) ≠ Admin (governance). Admin keeps org administration; GM keeps all

operations but loses governance.

Current state: admin and manager carry near-identical broad company-scoped permission sets.

Exact permission differences (target):

| Capability (permission) | Company Admin | GM (now) | GM (target) |
| --- | --- | --- | --- |
| settings.users (staff / role admin) | ✅ | ✅ | ❌ |
| settings.branches (branches/regions) | ✅ | ✅ | ❌ |
| settings.custom_fields (fields/data) | ✅ | ✅ | ❌ |
| integrations.manage (import/export/integrations) | ✅ | ✅ | ❌ |
| user.import / user.transfer | ✅ | ✅ | ❌ |
| workflow.manage | ✅ | ✅ | ❌ |
| — operations (unchanged) — |  |  |  |
| sales.sell / sales.collect / sales.credit | ✅ | ✅ | ✅ |
| customers.approve / customers.manage | ✅ | ✅ | ✅ |
| day.approve_close_exception / visit.approve_out_of_route | ✅ | ✅ | ✅ |
| reconciliation.manage / target.manage | ✅ | ✅ | ✅ |
| inventory.* / purchasing.manage | ✅ | ✅ | ✅ |
| accounting.view / accounting.post | ✅ | ✅ | ✅ |
| reports.view / report.aggregate.view | ✅ | ✅ | ✅ |

Net effect: GM loses Settings → Staff/Branches/Regions/Custom-Fields/Integrations and user-admin; keeps

the full operational + reporting + approvals surface. Admin is the only tenant role with governance.

Tasks: edit the manager company-scoped override on the DEMO tenant; mirror in reference-company.sql

+ new-tenant-bootstrap.sql (so new tenants inherit the split) and/or the global manager defaults.

Produce the before/after matrix (above). Regression-check that no operational flow relied on manager

holding settings.*.

Effort: ~1d · Deps: none (do early; clarifies the hierarchy for P1.5 QA) · Acceptance: GM login

shows no Settings-admin/Integrations items; all operational screens intact; matrix delivered.

Risk: 🟡 a flow that assumed manager == admin breaks — mitigate with the regression check + QA.

## 3. P1.3 — Collection Officer workspace

Objective: a dedicated Collections screen so a Collection Officer works AR directly (today collections

are only reachable via Invoices/Settlement).

Scope of the new `/collections` screen:

Open invoices — unpaid / partially-paid invoices (with aging buckets), filtered to the officer's scope.

Customer balances — AR per customer (erp_customers.balance), outstanding totals, last payment.

Collection workflow — "Record collection" → calls existing erp_settle_collection RPC (amount,

method, optional specific-invoice allocation), shows resulting allocation + new balance; supports partial

and full settlement; printable receipt (optional).

Tasks: new route /collections + nav item (gated sales.collect, distribution/sales section); server

loader (customers with balance > 0, open invoices, recent collections); client manager UI; a server action

wrapping erp_settle_collection; i18n (en/ar). Reuse existing settlement components where possible.

Effort: ~3d · Deps: none (RPC + data exist) · Acceptance: Collection Officer sees open

invoices + balances, records a partial and a full collection, and the customer balance + allocation update

correctly (ties to the seeded AR).

Risk: 🟡 allocation/double-apply correctness — rely solely on erp_settle_collection (already

idempotency-keyed); add a test on the demo AR.

## 4. P1.4 — Inventory Controller role (separate from Warehouse Manager)

Objective: a stock-accuracy role distinct from Warehouse Manager (today both map to warehouse_keeper).

Exact definition (target `inventory_controller`):

| Permission | Warehouse Manager (warehouse_keeper) | Inventory Controller (new) |
| --- | --- | --- |
| inventory.view / stock.view / product.search | ✅ | ✅ |
| inventory.count / inventory.adjust | ✅ | ✅ |
| stock.transfer / stock_request.approve | ✅ | ✅ |
| reconciliation.view | ✅ | ✅ |
| inventory.adjustment.approve / stock.transfer.approve | ✅ | ❌ (stock controller proposes, manager approves) |
| reconciliation.manage | ✅ | ❌ (view only) |
| purchasing.manage (Purchase Orders) | ✅ | ❌ |
| uom.manage | ✅ | ❌ |
| fashion.inventory / fashion.purchase | ✅ (latent) | ❌ |

Screens: Inventory (Products view, Stock, Low-stock, Expiry, Stock Count, Transfers, Warehouses

view), Van Reconciliation (view). No Purchase Orders, no Suppliers, no approval of

adjustments/transfers.

Tasks: add inventory_controller to erp_roles (+ company-scoped perms); remap the

inventory.controller@ demo user from warehouse_keeper; bake into reference-company.sql +

new-tenant-bootstrap.sql; deliver the matrix above.

Effort: ~1.5d · Deps: none (quick; mirrors the earlier refined-role pattern) · Acceptance:

Inventory Controller can count/adjust/transfer and view reconciliation, but cannot approve

adjustments, manage purchase orders, or see suppliers.

Risk: 🟢 low; ensure the new role has company-scoped perms (no global default exists → would otherwise

see nothing, same class of issue as the other refined roles).

## 5. P1.5 — Full role QA from the actual UI

Objective: validate every role in the running app — menus, screens, buttons, actions, write permissions —

not just DB/code inference.

Method: log in as each demo user on the QA build (P1.0) and walk a fixed checklist; log

expected-vs-actual per screen; file defects.

Coverage matrix (15 roles × screen set): Platform Owner, Company Admin, GM, Sales Manager, Area Manager,

Supervisor, Van Sales Rep, Cash Van Rep, Merchandiser, Warehouse Manager, Inventory Controller, Accountant,

Collection Officer, Credit Controller, Auditor — each checked for: visible menus; reachable screens (no

403/blank); action buttons present only when permitted; write actions succeed only when permitted

(attempt a forbidden write → must be blocked at API/RLS, not just hidden); data scope correct (rep sees own

customers, etc.).

Tasks: build a per-role checklist; execute; record results; raise fixes (expected to be small after

P1.1–P1.4). Deliver a QA results log + defect list.

Effort: ~2.5d · Deps: P1.0 (reachable build) + P1.1–P1.4 done (so QA validates final state)

· Acceptance: every role's menus/actions match the role spec; forbidden writes are rejected

server-side; defect list triaged.

Risk: 🟡 requires a reachable build; 🟡 may surface button-level gaps (e.g., a write button shown to a

read-only role) needing small fixes — budget a follow-up fix pass.

## 6. P1.6 — Mobile FMCG validation

Objective: validate the field experience on a phone for Van Rep, Cash Van, Merchandiser, Supervisor.

Scope per role:

Van Rep / Cash Van: Rep App / Today, GPS check-in, van stock, sell (cash; credit for van rep only),

collect, return, day-close/settlement; offline tolerance (queue + sync).

Merchandiser: visits, assortment/survey/grading capture, no selling.

Supervisor: team view, approvals, reconciliation on mobile.

Tasks: run the flows on a real device (and responsive web); verify offline queue/sync, GPS, and that the

cash-van credit option is hidden; log issues; triage fixes.

Effort: ~2.5d · Deps: P1.0 (reachable build); can run in parallel with P1.5 · Acceptance:

a rep can complete a full day on a phone (incl. an offline stretch) and data syncs consistently; cash-van

cannot create credit.

Risk: 🟠 mobile/offline is the least-validated area — expect to find issues; device/browser matrix and

offline edge-cases may extend effort.

## 7. Priority order, sequencing & effort

Recommended order (quick wins → foundational → QA):

| # | Task | Effort | Depends on |
| --- | --- | --- | --- |
| 1 | P1.0 Reachable QA build | 1d | — |
| 2 | P1.2 GM ⁄ Admin split | 1d | — |
| 3 | P1.4 Inventory Controller role | 1.5d | — |
| 4 | P1.1 Company Admin governance | 5–6d | — (security review gate) |
| 5 | P1.3 Collections workspace | 3d | — |
| 6 | P1.5 Full role QA | 2.5d | P1.0 + P1.1–P1.4 |
| 7 | P1.6 Mobile validation | 2.5d | P1.0 (∥ with P1.5) |

Critical path: P1.0 → P1.1/P1.2/P1.4/P1.3 → P1.5 (+P1.6 in parallel).

Total effort: ≈ 16–17 dev-days (~3–3.5 weeks solo; ~2 weeks with two engineers — one on P1.1, one on

P1.3/P1.4 — then converge on QA). P1.2 and P1.4 are quick wins to land first.

## 8. Dependency graph (summary)

P1.0 (reachable build) ─┬──────────────► P1.5 (role QA) ◄── P1.1, P1.2, P1.3, P1.4
                        └──────────────► P1.6 (mobile QA)
P1.2 (GM split)  ─ independent ─► (clarifies hierarchy for QA)
P1.4 (Inv Ctrl)  ─ independent
P1.1 (governance)─ independent (security review gate)
P1.3 (collections)─ independent

## 9. Risk register

| ID | Risk | Sev | Item | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Cross-tenant privilege escalation via new admin write paths | 🔴 | P1.1 | Gate every write on erp_is_company_admin(company_id) + erp_user_company_id(); 2-tenant negative test; keep role-key creation platform-only |
| R2 | Removing perms from GM breaks an operational flow | 🟡 | P1.2 | Regression check + QA; remove only governance perms |
| R3 | Collection allocation double-apply / balance drift | 🟡 | P1.3 | Use erp_settle_collection only (idempotency-keyed); reconcile against seeded AR |
| R4 | New role with no company perms → user sees nothing | 🟢 | P1.4 | Seed company-scoped perms (same pattern as refined roles) |
| R5 | QA/mobile blocked — no reachable build (SSO/egress) | 🟠 | P1.5/6 | P1.0 first (password-protected public URL) |
| R6 | Mobile/offline defects extend effort | 🟠 | P1.6 | Time-box; triage to a follow-up if non-blocking for pilot |
| R7 | Seed vs live vs global drift (perms defined in 3 places) | 🟡 | P1.1/2/4 | Single source: update DEMO + reference-company.sql + new-tenant-bootstrap.sql together |

## 10. Definition of Done (Phase 1)

Company Admin manages Branches / Users / Roles & Permissions / Warehouses within the tenant, with a

passing 2-tenant isolation test.

GM is operations-only; Admin holds governance; before/after matrix signed off.

Collection Officer has a working Collections workspace (open invoices, balances, settle).

Inventory Controller is a distinct, narrower role with its own screens.

A completed per-role UI QA log (15 roles) with forbidden writes rejected server-side.

A mobile validation log for Van Rep / Cash Van / Merchandiser / Supervisor.

All permission changes reflected in the DEMO tenant and the provisioning seeds.

Outcome: Phase 1 lifts FMCG pilot readiness from ~70% to an estimated ~85–90% (remaining:

dashboard/report validation and production cutover, per the assessment roadmap).